## Sheet1
Project ID: | SauceDemo_001 | Project Name : Swag labs
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
DF_SD_001 | User Login | In the login page there are some Accepted usernames are given in which locked_out_user username was not allowing user to login | Detailed Description: In the login page there are some "Accepted usernames" are given in which locked_out_user username was not allowing user to login (as per my assumption locked_out_user is a username which was given in registration) Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Enter Username 4. Enter Password 5. Click on Login button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the locked_out_user username is unable to login the user to the web page displaying various items available on the Swag labs as expected. | Coding | Google Chrome | Internal Dev | P2 | Medium | 1.2.4 | 4 | 2019-05-08 | Rasika Kundar |  | ACT |  | TC_SD_03
DF_SD_002 | User Login | Using the problem_user username the login is done properly but the image and information is not displayed properly | Detailed Description: Using the "problem_user" username the login is done properly but the image and information is not displayed properly Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Enter Username 4. Enter Password 5. Click on Login button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the "problem_user" username is able to login the user but unavailable to display the image and the information is not displayed as per the details on the Swag labs as expected. | Design | Google Chrome | Internal Dev | P2 | Medium | 1.2.4 | 4 | 2019-07-08 | Rasika Kundar |  | ACT |  | TC_SD_04
DF_SD_003 | Home Page | Using the problem_user username the login is done properly but the items are not added in the cart and the remove option is not displayed | Detailed Description: Using the problem_user username the login is done properly but the items are not added in the cart and the remove option is not displayed Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Enter Username 4. Enter Password 5. Click on Login button 6. Select the items Actual result observed on running above steps: On executing the above mentioned steps it is observed that the "problem_user" username is able to login the user but unable to add the items in cart and remove option is not displayed on the Swag labs as expected. | Coding | Google Chrome | Internal Dev | P1 | High | 1.2.4 | 4 | 2019-07-08 | Rasika Kundar |  | ACT |  | TC_SD_08
DF_SD_004 | Home Page | Using the problem_user username the login is done properly but the Remove option should remove the items from the Cart and display the option of "Add to Cart" in Home Page | Detailed Description: Using the problem_user username the login is done properly but the Remove option should remove the items from the Cart and display the option of "Add to Cart" in Home Page Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Enter Username 4. Enter Password 5. Click on Login button 6. Select the items 7. Click Remove in Home Page Actual result observed on running above steps: On executing the above mentioned steps it is observed that the "problem_user" username is able to login the user but unable to remove the items from cart on the Swag labs as expected. | Coding | Google Chrome | Internal Dev | P1 | High | 1.2.4 | 4 | 2019-07-08 | Rasika Kundar |  | ACT |  | TC_SD_10
DF_SD_005 | Cart Page | User is able to login properly but user is unable to increase the quantity of same item | Detailed Description: User is able to login properly but user is unable to increase the quantity of same item Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Enter Username 4. Enter Password 5. Click on Login button 6. Select the items Actual result observed on running above steps: On executing the above mentioned steps it is observed that the login is done properly by the user but unable to increase the quantity of same item on the Swag labs as expected. | Coding | Google Chrome | Internal Dev | P2 | Medium | 1.2.4 | 4 | 2019-07-08 | Rasika Kundar |  | ACT |  | TC_SD_11
DF_SD_006 | Home Page | Using the problem_user username the login is done properly but the filter is not done as per the option available | Detailed Description: Using the problem_user username the login is done properly but the filter is not done as per the option available Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Enter Username 4. Enter Password 5. Click on Login button 6. Select the Filter DropDown Actual result observed on running above steps: On executing the above mentioned steps it is observed that the login is done properly by the user but the filter is not done as per the option available on the Swag labs as expected. . | Coding | Google Chrome | Internal Dev | P3 | Low | 1.2.4 | 4 | 2019-08-08 | Rasika Kundar |  | ACT |  | TC_SD_13
DF_SD_007 | Checkout Page | Using the problem_user username the login is done properly but the information given while checking out is not done properly | Detailed Description: Using the problem_user username the login is done properly but the information given while checking out is not done properly Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Enter Username 4. Enter Password 5. Click on Login button 6. Select the items 7. Select Checkout option Actual result observed on running above steps: On executing the above mentioned steps it is observed that the login is done properly by the user but the information given from user is not taken properly on the Swag labs as expected. | Coding | Google Chrome | Internal Dev | P1 | High | 1.2.4 | 4 | 2019-08-08 | Rasika Kundar |  | ACT |  | TC_SD_14
DF_SD_008 | Cart Page | User is able to login properly but user is unable to reset the application when selecting the reset option | Detailed Description: User is able to login properly but user is unable to reset the application when selecting the reset option Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Enter Username 4. Enter Password 5. Click on Login button 6. Select the items 7. Click on Reset App Store Actual result observed on running above steps: On executing the above mentioned steps it is observed that the login is done properly by the user but is unable to reset the entire application on the Swag labs as expected. . | Coding | Google Chrome | Internal Dev | P1 | High | 1.2.4 | 4 | 2019-09-08 | Rasika Kundar |  | ACT |  | TC_SD_15
DF_SD_009 | Cart Page | User is able to login properly but user is unable to check whether the items are selected in cart while further clicking on checkout option | Detailed Description: User is able to login properly but user is unable to check whether the items are selected in cart while further clicking on checkout option Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Enter Username 4. Enter Password 5. Click on Login button 6. Select Checkout option Actual result observed on running above steps: On executing the above mentioned steps it is observed that the login is done properly by the user but is unable to verify that the items are selected after clicking on checkout option on the Swag labs as expected. . | Coding | Google Chrome | Internal Dev | P2 | Medium | 1.2.4 | 4 | 2019-09-08 | Rasika Kundar |  | ACT |  | TC_SD_16
DF_SD_010 | Checkout Page | Using the problem_user username the login is done properly but the calculation done at the end is not properly calculated | Detailed Description: Using the problem_user username the login is done properly but the calculation done at the end is not properly calculated Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Enter Username 4. Enter Password 5. Click on Login button 6. Select the items 7. Select Checkout option Actual result observed on running above steps: On executing the above mentioned steps it is observed that the login is done properly by the user but the calculation in end is not done correctly on the Swag labs as expected. | Coding | Google Chrome | Internal Dev | P1 | High | 1.2.4 | 4 | 2019-10-08 | Rasika Kundar |  | ACT |  | TC_SD_17
DF_SD_011 | Checkout Page | User is able to login properly but user is unable to get the payment method | Detailed Description: User is able to login properly but user is unable to get the payment method Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Enter Username 4. Enter Password 5. Click on Login button 6. Select the items 7. Select Checkout option Actual result observed on running above steps: On executing the above mentioned steps it is observed that the login is done properly by the user but there is no payment method optio available to user on the Swag labs as expected. | Coding | Google Chrome | Internal Dev | P2 | Medium | 1.2.4 | 4 | 2019-10-08 | Rasika Kundar |  | ACT |  | TC_SD_18
Note on A3: Alphy Chenganiyadan Give a unique number for the Defect Id
Note on B3: Alphy Chenganiyadan: Give the name of the module being tested
Note on C3: Alphy Chenganiyadan: Summarize the defect in 1 or 2 lines
Note on D3: Alphy Chenganiyadan: A detailed description of the defect
Note on E3: Alphy Chenganiyadan: Categorize the defect into the one of the values given in the drop down list
Note on F3: Alphy Chenganiyadan: Mention the name of the browser the defect was found in.
Note on G3: Alphy Chenganiyadan: Mention the environment in which the defect was found.
Note on H3: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I3: Prioritize the defect
Note on J3: Alphy Chenganiyadan: Enter the Release # in which the defect was detected.
Note on K3: Alphy Chenganiyadan: Enter the Build # in which the defect was detected.
Note on L3: Alphy Chenganiyadan: Mention the date the defect was reported
Note on M3: Alphy Chenganiyadan: Name of the person who reported the defect.
Note on N3: Alphy Chenganiyadan: Name of the person the defect is assigned to.
Note on O3: Alphy Chenganiyadan: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P3: Alphy Chenganiyadan: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q3: Alphy Chenganiyadan: Mention the Test Case No that the defect was found while testing
Note on R3: Alphy Chenganiyadan: Name of the person who fixed the defect.
Note on S3: Alphy Chenganiyadan: Mention the date the defect was Fixed
Note on T3: Alphy Chenganiyadan: Mention the date the defect was verified
Note on U3: Alphy Chenganiyadan: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V3: Alphy Chenganiyadan: Enter the Release # in which the defect was available for verification
Note on W3: Alphy Chenganiyadan: Enter the Build # in which the defect was available for verification
Note on X3: Alphy Chenganiyadan: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y3: Alphy Chenganiyadan: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.